PART E: WORK PLAN (Revised version, 30.9.2010)

| Project: EMAP 2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stage in life of project | Outputs: By the end of this stage we will have achieved / produced | Activities leading to this output | Activities to be started by this date and completed by this date Start Complete | Partners / Persons involved | Time input (person/days or person/months) |

| 1 Preparation of the kick-off project meeting | Meeting agenda and documents sent to participants | Email communication of the management team Preparing the content and supporting documentation of the meeting | 01/10/10 |  | 26/10/10 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 2 person/day = 14 person/day in total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2 Organization of the kick-off project meeting | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 01/10/10 |  | 26/10/10 | LT, CZ | LT: 3 person/day CZ: 2 person/day 5 person/day in total |
| 3 Kick-off project meeting in Lithuania (after the project meeting partners will have a chance to stay for the JOIMAN conference as a training and capacity building event) | Agreement on the issues for discussion Report from the meeting | Discussion about the following issues: 1/ criteria for identification and selection of consortia for training seminars; 2/ criteria for identification and selection of experienced EMMC and EMJD representatives; requirements on their presentations 3/ content, agenda and logistics of training seminars; 4/ identification of EM NS training needs and possible trainers / external experts; 5/ creation of a virtual EM NS social network; 6/ content of the project website; 7/ analysis of the last EM Action 1 selection results with regards to the EMAP 1 project. | 27/10/10 |  | 28/10/10 | All project partners | 17 partners: each 1 person/day = 17 person/day in total |
| 4 Identification of potential EMMC consortia for training seminars in the first year and pre-seminar consultations | Two consortia for each country concerned are identified and prepared for training seminars | Individual search or call for existing or potential joint study programmes in countries concerned Possible applicants contacted, consulted and nominated to the first two EMMC training seminars | 30/10/10 |  | 31/12/10 | AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK | AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK: each 2x 4 person/day = 88 person/day in total |
| 5 Identification of experienced EMMC representatives for training seminars in the first year and pre-seminar instructions | Experienced EMMC representatives selected and instructed | Individual search of potential good practice EMMC representatives Possible representatives contacted, consulted and nominated to the first two EMMC training seminars | 30/10/10 |  | 31/12/10 | AT, FR, HU, NL, NO, SI | AT, FR, HU, NL, NO, SI: each 2 person/day = 12 person/day in total |
| 6 Project website and EM NS social network launch | Launching the website and network with all its tools following the EM NS requirements | Development and set up of the website and network | 30/10/10 |  | 31/01/11 | IT team (CZ, LT) | CZ, LT: each 5 person/day = 10 person/day in total |
| 7 Preparation of the presentations and training material for the EMMC training seminars in Poland and Latvia and for the training session for EM NS in Poland | Presentations, training material and lectures | Distribution of tasks among trainers Identification and addressing external experts for EM NS training session if needed Preparation of presentations and training materials | 30/10/10 |  | 15/01/11 | Training team (AT, BE, DE, FI, FR, NO) | AT, BE, DE, FI, FR, NO: each 6 person/day = 36 person/day in total |
| 8 Preparation of the first EMMC training seminar and training session for EM NS in Poland | Agenda and all documents sent to participants and available at project website | Email communication of the management team Preparing the content and supporting documentation of the event | 30/10/10 |  | 15/01/11 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 2 person/day = 14 person/day in total |
| 9 Organization of the EMMC training seminar in Poland | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 30/10/10 |  | End Jan 2011 | PL, CZ | PL: 10 person/day CZ: 4 person/day 14 person/day in total |
| 10 First EMMC training seminar and training session for EM NS in Poland | Seminar implemented | One day of EM NS training Two days of potential EMMC consortia training | End Jan 2011 |  |  | All project partners | No working hours calculated, event is meant as a training and capacity building, working hours for trainers and organisers are included under points 7, 8 and 9 |
| 11 Preparation of the second EMMC training seminar in Latvia | Agenda and all documents sent to participants and available at project website | Email communication of the management team Preparing the content and supporting documentation of the event | 30/10/10 |  | 15/02/11 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 2 person/day = 14 person/day in total |
| 12 Organization of the EMMC training seminar in Latvia | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 30/10/10 |  | Early Mar 2011 | LV, CZ | LV: 10 person/day CZ: 4 person/day 14 person/day in total |
| 13 Second EMMC training seminar in Latvia | Seminar implemented | Two days of potential EMMC consortia training | Early Mar 2011 |  |  | All project partners (except NL) | No working hours calculated, event is meant as a training and capacity building, working hours for trainers and organisers are included under points 7, 11 and 12 |
| 14 Evaluation of EMMC training seminars in Poland and Latvia and of the training session for EM NS in Poland | Questionnaires´ evaluation Reports on the seminars | Analysis of participants´ satisfaction according to the questionnaires Collecting main outputs and recommendations | 15/03/11 |  | 15/05/11 | Reporting team (CY, EE, GR, SK) | CY, EE, GR, SK: each 6 person/day = 24 person/day in total |
| 15 Evaluation of the EMMC application submitted | Analysis of applications submitted and selected | Examination of the results of the relevant Erasmus Mundus Call for Proposal with focus on countries that sent consortia to training seminars in Poland and Latvia | 01/07/11 | 30/09/11 |  | AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK | AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK: each 1 person/day = 11 person/day in total |
| 16 Preparation of the mid-term project meeting | Meeting agenda and documents sent to participants | Email communication of the management team Preparing the content and supporting documentation of the meeting | 01/09/11 | Mid Oct 2011 |  | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 1 person/day = 7 person/day in total |
| 17 Organization of the mid-term project meeting | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 01/09/11 | Mid Oct 2011 |  | HU, CZ | HU: 3 person/day CZ: 2 person/day 5 person/day in total |
| 18 Mid-term project meeting in Hungary | Agreement on the issues for discussion Report from the meeting | Discussion about the following issues: 1/ analysis of the last EM Action 1 selection results; 2/ need of adjustments regarding the training seminars´ content, participants selection etc. 3/ identification of EM NS training needs and possible trainers / external experts; 4/ mid-term project evaluation and progress report for the EACEA; 5/ dissemination activities. | Mid Oct 2011 |  |  | All project partners | 17 partners: each 1 person/day = 17 person/day in total |
| 19 Identification of potential EMMC and EMJD consortia for training seminars in the second year and pre-seminar consultations | Two consortia for each country concerned are identified and prepared for training seminars | Individual search or call for existing or potential joint study programmes in countries concerned Possible applicants contacted, consulted and nominated to the EMMC and EMJD training seminars | 30/10/11 |  | 31/12/11 | AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK (EMMC) AT, BE, CY, CZ, DE, EE, FI, GR, HU, LT, LV, NL, PL, SI, SK (EMJD) | EMMC: AT, CY, CZ, EE, GR, HU, LT, LV, PL, SI, SK: each 4 person/day = 44 person/day in total EMJD: AT, BE, CY, CZ, DE, EE, FI, GR, HU, LT, LV, NL, PL, SI, SK: each 4 person/day = 60 person/day in total |
| 20 Identification of experienced EMMC and EMJD representatives for training seminars in the second year and pre-seminar instructions | Experienced EMMC and EMJD representatives selected and instructed | Individual search of potential good practice EMMC and EMJD representatives Possible representatives contacted, consulted and nominated to the EMMC and EMJD training seminars | 30/10/11 |  | 31/12/11 | BE, DE, PL (EMMC) AT, FR, NL (EMJD) | BE, DE, PL, AT, FR, NL: each 2 person/day = 12 person/day in total |
| 21 Preparation of the presentations and training material for the EMMC and EMJD training seminars in Estonia and Slovenia and for the training session for EM NS in Estonia | Presentations, training material and lectures | Distribution of tasks among trainers Identification and addressing external experts for EM NS training session if needed Preparation of presentations and training materials | 30/10/11 |  | 15/01/12 | Training team (AT, BE, DE, FI, FR, NO) | AT, BE, DE, FI, FR, NO: each 6 person/day = 36 person/day in total |
| 22 Preparation of the EMJD training seminar and training session for EM NS in Estonia | Agenda and all documents sent to participants and available at project website | Email communication of the management team Preparing the content and supporting documentation of the event | 30/10/11 |  | 15/01/12 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 2 person/day = 14 person/day in total |
| 23 Organization of the EMJD training seminar in Estonia | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 30/10/11 |  | End Jan 2012 | EE, CZ | EE: 10 person/day CZ: 4 person/day 14 person/day in total |
| 24 EMJD training seminar and training session for EM NS in Estonia | Seminar implemented | One day of EM NS training Two days of potential EMJD consortia training | End Jan 2012 |  |  | All project partners | No working hours calculated, event is meant as a training and capacity building, working hours for trainers and organisers are included under points 21, 22 and 23 |
| 25 Preparation of the EMMC training seminar in Slovenia | Agenda and all documents sent to participants and available at project website | Email communication of the management team Preparing the content and supporting documentation of the event | 30/10/11 |  | 15/02/12 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 2 person/day = 14 person/day in total |
| 26 Organization of the EMMC training seminar in Slovenia | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 30/10/11 |  | Early Mar 2012 | SI, CZ | SI: 10 person/day CZ: 4 person/day 14 person/day in total |
| 27 Third EMMC training seminar in Slovenia | Seminar implemented | One day of EM NS training Two days of potential EMMC consortia training | Early Mar 2012 |  |  | All project partners (except NL) | No working hours calculated, event is meant as a training and capacity building, working hours for trainers and organisers are included under points 21, 25 and 26 |
| 28 Evaluation of EMMC and EMJD training seminars in Estonia and Slovenia and of the training session for EM NS in Estonia | Questionnaires´ evaluation Reports on the seminars | Analysis of participants´ satisfaction according to the questionnaires Collecting main outputs and recommendations | 15/03/12 |  | 15/05/12 | Reporting team (CY, EE, GR, SK) | CY, EE, GR, SK: each 6 person/day = 24 person/day in total |
| 29 Evaluation of the EMMC and EMJD application submitted | Analysis of applications submitted and selected | Examination of the results of the relevant Erasmus Mundus Call for Proposal with focus on countries that sent consortia to training seminars in Estonia and Slovenia | 01/07/12 |  | 15/08/12 | AT, BE, CY, CZ, DE, EE, FI, GR, HU, LT, LV, NL, PL, SI, SK | AT, BE, CY, CZ, DE, EE, FI, GR, HU, LT, LV, NL, PL, SI, SK: each 1 person/day = 15 person/day in total |
| 30 Preparation of the final project meeting | Meeting agenda and documents sent to participants | Email communication of the management team Preparing the content and supporting documentation of the meeting | 01/05/12 |  | 30/05/12 | Management team (AT, BE, CZ, DE, HU, LT, SK) | AT, BE, CZ, DE, HU, LT, SK: each 1 person/day = 7 person/day in total |
| 31 Organization of the final project meeting | Seminar set up | Seminar logistics (meeting room, accommodation, meals and folders for participants) Registration of participants | 01/05/12 |  | Mid Jun 2012 | CZ | CZ: 3 person/day in total |
| 32 Final project meeting in the Czech Republic | Agreement on the issues for discussion Report from the meeting | Discussion about the following issues: 1/ analysis of the last EM Action 1 application results; 2/ project evaluation and final report for the EACEA; 3/ dissemination activities; 4/ follow-up and sustainability of the project, exploitation of the project results. | Mid Jun 2012 |  |  | All project partners | 17 partners: each 1 person/day = 17 person/day in total |
| 33 Dissemination activities | Raised awareness about the project results All project information and documentation available at project website | Gathering documents for further dissemination Carrying out dissemination at project, national and international levels Feeding and updating the project website content | Continuously |  |  | All project partners Special tasks for IT team (CZ, LT) | 17 partners: each 2 person/day = 34 person/day in total CZ, LT: each 5 person/day = 10 person/day in total |
| 34 Project management | Sound management of the project | Managing the project activities Ensuring smooth communication and tasks distribution among the partners Financial management Reporting to EACEA and preparing reports from the project meetings Monitoring, controlling and documentation activities | Continuously |  |  | CZ | CZ: 30 person/day in total |