## Annex_EMAP2_tasks
Annex to the EMAP 2 Application Form: DISTRIBUTION OF TASKS AMONG PARTNERS, incl. number of person/days
| AT | BE | CY | CZ | DE | EE | FI | FR | GR | HU | LT | LV | NL | NO | PL | SI | SK
| 1 | 2 | 3 | Coordinator | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Identification and selection of consortia for 3 EMMC training seminars, incl. consultations and preparation activities | 12 |  | 12 | 12 |  | 12 |  |  | 12 | 12 | 12 | 12 |  |  | 12 | 12 | 12
Identification and selection of consortia for 1 EMJD training seminar, incl. consultations and preparation activities | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 4
Participation in the management team (drafting content of events and documentation, project monitoring, closer cooperation with coordinator) | 12 | 12 |  | 12 | DE 4: 12; HU 9: 12; LT 10: 12; SK 16: 12
Organizing a 3 day training seminar (2011: PL and LV, 2012: EE and SI) |  |  |  |  | EE 5: 10; LV 11: 10; PL 14: 10; SI 15: 10
Organizing a 1 day project meeting (kick-off in LT together with Joiman conference, mid-term in HU together with NS informal meeting, final in CZ) |  |  |  | 3 | HU 9: 3; LT 10: 3
Participation in 3 project meetings | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Identification and selection of 1 good practice EMMC | 2 | 2 |  |  | DE 4: 2; FR 7: 2; HU 9: 2; NL 12: 2; NO 13: 2; PL 14: 2; SI 15: 2
Identification and selection of 1 good practice EMJD | 2 |  |  |  | FR 7: 2; NL 12: 2
Participation in the training team (acting as trainer during consortia and NS seminars, identification of NS training needs, preparation of presentations, addressing external experts if needed) | 12 | 12 |  |  | DE 4: 12; FI 6: 12; FR 7: 12; NO 13: 12
Participation in the IT team (terms of reference for project website and NS communication tool, set up, publishing of documents and events) |  |  |  | 10 | LT 10: 10
Dissemination activities | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Participation in the reporting team (reporting from the 4 training seminars, collecting main outputs and recommendations, analysis of questionnaires) |  |  | 12 |  | EE 5: 12; GR 8: 12; SK 16: 12
Evaluation activities (analysis of calls results) | 2 | 1 | 2 | 2 | 1 | 2 | 1 |  | 2 | 2 | 2 | 2 | 1 |  | 2 | 2 | 2
Project management (reporting from project meetings, financial management, progress and final reports...) |  |  |  | 50
Total person/days | 51 | 36 | 35 | 98 | 36 | 45 | 22 | 21 | 35 | 40 | 48 | 33 | 14 | 19 | 35 | 35 | 47 | 650